## Gantt Chart
PHILA FIRE
PROJECT TITLE |  | [Project's title]
PROJECT MANAGER |  | [Project Manager's name]
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE - EXPLORATPRY ANALYSIS | [19 empty] | PHASE TWO - MODELING | [14 empty] | PHASE THREE - APP DEVELOPMENT
[7 empty] | WEEK 1 - 1/16 |  |  |  |  | WEEK 2 - 1/23 |  |  |  |  | WEEK 3 - 1/30 |  |  |  |  | WEEK 4 - 2/6 |  |  |  |  | WEEK 5 -2/13 |  |  |  |  | WEEK 6 - 2/20 |  |  |  |  | WEEK 7 - 2/27 |  |  |  |  | WEEK 9 - 3/13 |  |  |  |  | WEEK 10 - 3/20 |  |  |  |  | WEEK 11 - 3/27 |  |  |  |  | WEEK 12 - 4/3 |  |  |  |  | WEEK 13 - 4/10 |  |  |  |  | WEEK 14 - 4/17
[7 empty] | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 1 | 2 | 3 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25
1 | Data Wrangling
1.1 | Load data into R | bar: WEEK 2 - 1/23 23 to WEEK 2 - 1/23 27
1.2 | Clean structure Fires Spatialized | bar: WEEK 2 - 1/23 24 to WEEK 4 - 2/6 8
1.3 | Geocoding (if necessary) | bar: WEEK 4 - 2/6 7 to WEEK 4 - 2/6 10
2 | Exploratory Analysis
2.1 | Research Data Sources | bar: WEEK 3 - 1/30 1 to WEEK 5 -2/13 16
2.2 | Combine Data Sources | bar: WEEK 4 - 2/6 8 to WEEK 5 -2/13 16
2.3 | Correlation Plots | bar: WEEK 5 -2/13 14 to WEEK 5 -2/13 16
2.4 | Establish Clustering | bar: WEEK 5 -2/13 14 to WEEK 5 -2/13 16
2.5 | Determine X Variable | bar: WEEK 5 -2/13 14 to WEEK 5 -2/13 16
2.6 | Anecdotal Research | bar: WEEK 3 - 1/30 30 to WEEK 6 - 2/20 20; WEEK 6 - 2/20 22 to WEEK 7 - 2/27 3
2.7 | Interview Coordination (If Necessary) | bar: WEEK 7 - 2/27 28 to WEEK 7 - 2/27 3
3 | Modeling
3.1 | Modeling Iteration | bar: WEEK 5 -2/13 15 to WEEK 6 - 2/20 20; WEEK 6 - 2/20 22
3.2 | Establish Modeling Strategy | bar: WEEK 6 - 2/20 20; WEEK 6 - 2/20 22
3.3 | Intitial Cross Validation | bar: WEEK 6 - 2/20 20; WEEK 6 - 2/20 22
4 | App Development
4.1 | User Journey (Maybe) | bar: WEEK 7 - 2/27 1 to WEEK 7 - 2/27 3
4.2 | User Flow
4.3 | Information Architecture?
4.4 | Wireframing
4.5 | User Testing with Click-Through Prototype?
4.6 | Part 1 Prototype (Prediction Map)
4.7 | Part 2 Prototype (Stories)
4.8 | QA
4.9 | Evaluation and Revisions
5 | Submittal